## DIM_PM
PMID | PMNAME
2014 | Mourad Abu Asfar
2015 | Muaz Dahmas
2016 | Zainudheen
2017 | Muhammad Javed
2018 | Mohammed Naveed
2019 | Khalid.Abulfutuh
2020 | Mohamed Kamel
2021 | Afrah Mahayef

## DIM_CUSTOMER
CUSTOMERID | CUSTOMER_NAME
C001 | ALKAFAA REAL ESTATE COMPANY
C002 | SEC
C003 | Adwaa Alkhaleel Contracting Company.(SEC DDC IT Infrastructure)
C004 | PSS
C005 | Abdullah Mastour Al-Ghamdi Contracting Est
C006 | Golf Saudi
C007 | Digital & security shield
C008 | SAMI
C009 | SVC
C010 | Integrated Computer Systems (ICS)

## DIM_PROJECT_INFO
PROJECTCODE | CUSTOMERID | TECHID | PMID | BAC | PROJECTTYPE | PROJECTSUBTYPE | PROJECTCATEGOREY | PROJECTSTARTDATE | PROJECTFINSHDATE
LA-08 | C007 | TECH-INFRASTRUCTURE | 2015 | 100000000 | NA |  | NA | 2019-03-31 | 2022-03-31
NM-12 | C008 | TECH-VIDEOCONFERENCING | 2015 | 500000000 | NA |  | NA | 2019-06-30 | 2023-06-30
AM-02 | C001 | TECH-IOT | 2020 | 40000000 | NA |  | NA | 2021-05-15 | 2024-05-15
AT-01 | C002 | TECH-AI | 2019 | 54000000 | NA |  | NA | 2022-01-01 | 2023-08-01
BA-15 | C009 | TECH-RPA | 2017 | 50000000 | NA |  | NA | 2022-12-01 | 2023-06-05
BA-29 | C010 | TECH-BIGDATAANALYTICS | 2021 | 480000000 | NA |  | NA | 2019-08-09 | 2023-08-09

## DIM_TECHNOLOGY
TECHID | PROJECTCATEGOREY | ProjectType | Technology Name
TECH-INFRASTRUCTURE | INFRASTRUCTURE | Infrastructure | Servers, Storage, Network Devices, Routers, Switches
TECH-VIDEOCONFERENCING | VIDEOCONFERENCING | Video Conferencing | Zoom, Microsoft Teams, Webex, Skype, BlueJeans, GoToMeeting
TECH-AI | IOT | Artificial Intelligence (AI) | Machine Learning, Natural Language Processing, Computer Vision
TECH-RPA | AI | Robotics Process Automation (RPA) | UiPath, Automation Anywhere, Blue Prism, WorkFusion
TECH-BIGDATAANALYTICS | RPA | Big Data Analytics | Hadoop, Spark, Hive, Pig, Cassandra

## DIM_RISK
PROJECTCODE | RISKID | RiskCategory | RiskSubCategory | RiskProbability | RiskImpact | RISKSCORE
AM-02 | RSK-001 | Technical | Software | High | Medium | 60
AT-01 | RSK-020 | Operational | Supply Chain | Low | High | 20
BA-15 | RSK-015 | Financial | Market | Medium | High | 70
BA-29 | RSK-038 | Legal | Compliance | Low | Low | 10
LA-08 | RSK-022 | Human | Health and Safety | High | High | 90
NM-12 | RSK-010 | Operational | Regulatory Compliance | High | High | 85
AM-02 | RSK-011 | Operational | Supply Chain | Low | High | 20
AM-02 | RSK-002 | Financial | Market | Medium | High | 70
AM-02 | RSK-019 | Legal | Compliance | Low | Low | 10
AM-02 | RSK-017 | Human | Health and Safety | High | High | 90
AT-01 | RSK-024 | Financial | Fraud | High | High | 90
AT-01 | RSK-009 | Operational | Process Failure | Medium | Low | 30
AT-01 | RSK-007 | Environmental | Climate Change | Low | High | 40
AT-01 | RSK-035 | Technical | Cybersecurity | High | High | 80
AT-01 | RSK-036 | Human | Employee Turnover | Medium | Medium | 50
AT-01 | RSK-016 | Legal | Litigation | Low | Medium | 20
AT-01 | RSK-034 | Financial | Investment | Medium | High | 60
BA-15 | RSK-012 | Technical | Infrastructure | Low | High | 35
BA-15 | RSK-023 | Operational | Maintenance | High | Medium | 70
BA-15 | RSK-005 | Environmental | Pollution | Medium | High | 60
BA-15 | RSK-028 | Human | Discrimination and Harassment | Low | Low | 5
BA-15 | RSK-029 | Legal | Regulatory Compliance | High | High | 85
BA-15 | RSK-014 | Financial | Liquidity | Medium | Medium | 45
BA-29 | RSK-032 | Operational | Capacity | High | High | 90
BA-29 | RSK-040 | Financial | Tax | Medium | Medium | 50
BA-29 | RSK-006 | Environmental | Biodiversity | Low | High | 30
BA-29 | RSK-037 | Human | Labor Relations | Medium | Medium | 40
BA-29 | RSK-027 | Legal | Product Liability | High | High | 80
BA-29 | RSK-021 | Technical | System Integration | Medium | Low | 25
BA-29 | RSK-018 | Operational | Health and Safety | High | High | 90
BA-29 | RSK-030 | Financial | Inflation | Low | High | 35
BA-29 | RSK-033 | Environmental | Resource Depletion | Medium | Medium | 50
BA-29 | RSK-004 | Human | Diversity and Inclusion | Low | Low | 5
BA-29 | RSK-025 | Legal | Intellectual Property Infringement | Medium | High | 65
BA-29 | RSK-008 | Operational | Supply Chain Disruption | High | High | 85
BA-29 | RSK-031 | Financial | Interest Rate | Medium | Low | 20
BA-29 | RSK-013 | Technical | Data Security | High | High | 80
BA-29 | RSK-003 | Environmental | Natural Resource Scarcity | Low | High | 40
BA-29 | RSK-026 | Human | Organizational Culture | Medium | Medium | 55
BA-29 | RSK-039 | Legal | Contractual | Low | Low | 10
BA-29 | RSK-001 | Financial | Credit Rating | Medium | High | 60
LA-08 | RSK-041 | Operational | Logistics | Medium | Low | 20
LA-08 | RSK-054 | Financial | Foreign Exchange | High | Medium | 70
LA-08 | RSK-059 | Environmental | Extreme Weather | Low | High | 30
LA-08 | RSK-043 | Human | Employee Health | High | Medium | 60
LA-08 | RSK-046 | Legal | Labor Lawsuits | Low | High | 45
LA-08 | RSK-051 | Technical | Software Bugs | High | High | 85
LA-08 | RSK-049 | Operational | Production Downtime | High | Medium | 75
LA-08 | RSK-060 | Financial | Capital Markets | Medium | High | 80
LA-08 | RSK-057 | Environmental | Waste Management | Medium | Low | 15
LA-08 | RSK-044 | Human | Performance Management | Medium | Medium | 50
LA-08 | RSK-056 | Legal | Anti-Trust | Low | High | 55
LA-08 | RSK-058 | Operational | Project Management | Medium | Medium | 40
LA-08 | RSK-047 | Financial | Credit Risk | High | High | 90
NM-12 | RSK-050 | Financial | Default | High | High | 95
NM-12 | RSK-055 | Environmental | Air Pollution | Low | High | 40
NM-12 | RSK-053 | Human | Benefits Administration | Medium | Medium | 45
NM-12 | RSK-048 | Legal | Cyber Lawsuits | Low | Medium | 30
NM-12 | RSK-052 | Technical | Application Development | Medium | Medium | 50
NM-12 | RSK-045 | Operational | Business Continuity | High | High | 90
NM-12 | RSK-042 | Financial | Market Volatility | Medium | High | 70
NM-12 | RSK-012 | Environmental | Water Scarcity | Low | High | 35
NM-12 | RSK-023 | Human | Succession Planning | Medium | Medium | 40
NM-12 | RSK-005 | Legal | Privacy | Medium | High | 65
NM-12 | RSK-028 | Operational | Customer Service | Medium | Low | 15
NM-12 | RSK-029 | Operational | Regulatory Compliance | High | High | 85
NM-12 | RSK-014 | Financial | Default | High | High | 95
NM-12 | RSK-032 | Environmental | Air Pollution | Low | High | 40
NM-12 | RSK-040 | Human | Benefits Administration | Medium | Medium | 45
NM-12 | RSK-006 | Legal | Cyber Lawsuits | Low | Medium | 30
NM-12 | RSK-037 | Technical | Application Development | Medium | Medium | 50
NM-12 | RSK-027 | Operational | Business Continuity | High | High | 90
NM-12 | RSK-021 | Financial | Market Volatility | Medium | High | 70
NM-12 | RSK-018 | Environmental | Water Scarcity | Low | High | 35
NM-12 | RSK-030 | Human | Succession Planning | Medium | Medium | 40
NM-12 | RSK-033 | Legal | Privacy | Medium | High | 65
NM-12 | RSK-004 | Operational | Customer Service | Medium | Low | 15
NM-12 | RSK-025 | Financial | Currency Risk | High | High | 85
NM-12 | RSK-008 | Technical | IT Governance | Medium | Medium | 50
NM-12 | RSK-031 | Environmental | Deforestation | Low | High | 25
NM-12 | RSK-013 | Human | Workplace Safety | High | High | 80
AM-02 | RSK-003 | Legal | Contract Disputes | Low | Medium | 35
AM-02 | RSK-026 | Operational | Asset Management | Medium | Medium | 45
AM-02 | RSK-039 | Financial | Reputational Risk | Low | High | 30
AM-02 | RSK-001 | Technical | Internet Connectivity | High | Medium | 65
AM-02 | RSK-388 | Legal | Intellectual Property | High | High | 80

## DIM_ISSUE
PROJECTCODE | ISSUEID | ISSUEDDESCREPTION | ISSUESeverity | ISSUEAGE DAYS | ISSUEResolutionTime (days) | ISSUEReoccurrence | ISSUEClosure Rate
AM-02 | ISSU-004 | Production Line Downtime | High | 12 | 5 | Yes | 75%
AT-01 | ISSU-030 | Pollution Monitoring and Control | Medium | 30 | 45 | No | 95%
BA-15 | ISSU-078 | Employee Turnover and Retention | Medium | 60 | 90 | No | 80%
BA-29 | ISSU-090 | Intellectual Property Infringement Lawsuit | High | 180 | 240 | Yes | 60%
LA-08 | ISSU-004 | System Integration Failure | High | 2 | 3 | No | 40%
NM-12 | ISSU-030 | Supply Chain Disruption due to Natural Disaster | High | 14 | 21 | Yes | 50%
AM-02 | ISSU-078 | Inflation Impact on Raw Material Prices | Medium | 45 | 60 | No | 85%
AM-02 | ISSU-090 | Workplace Discrimination Complaint | Low | 7 | 14 | Yes | 70%
AM-02 | ISSU-005 | Product Liability Claim | High | 90 | 120 | Yes | 40%
AM-02 | ISSU-051 | Data Security Breach | High | 1 | 2 | Yes | 90%
AT-01 | ISSU-062 | Production Line Quality Control Issue | Medium | 5 | 7 | No | 80%
AT-01 | ISSU-076 | Interest Rate Impact on Borrowing Costs | Medium | 30 | 45 | No | 75%
AT-01 | ISSU-009 | Cloud Computing Outage | High | 3 | 4 | Yes | 85%
AT-01 | ISSU-068 | Extreme Weather Impact on Business Operations | High | 10 | 14 | Yes | 60%
AT-01 | ISSU-086 | Labor Lawsuit Settlement | Medium | 180 | 240 | Yes | 50%
AT-01 | ISSU-003 | Software Bug in Critical System | High | 1 | 1 | Yes | 100%
AT-01 | ISSU-029 | Business Continuity Planning and Disaster Recovery | High | 7 | 14 | No | 95%
BA-15 | ISSU-077 | Market Volatility Impact on Investment Portfolio | Medium | 60 | 90 | No | 80%
BA-15 | ISSU-040 | Deforestation Impact on Supply Chain | Low | 14 | 21 | Yes | 65%
BA-15 | ISSU-081 | Regulatory Non-Compliance Fine | High | 60 | 90 | No | 70%
BA-15 | ISSU-091 | Water Scarcity Impact on Manufacturing | High | 10 | 14 | Yes | 50%
BA-15 | ISSU-054 | Employee Training and Development | Medium | 30 | 45 | No | 90%
BA-15 | ISSU-018 | Cybersecurity Attack | High | 1 | 2 | Yes | 95%
BA-29 | ISSU-045 | Production Line Equipment Failure | Medium | 7 | 10 | No | 75%
BA-29 | ISSU-013 | Natural Gas Price Volatility | Medium | 14 | 21 | No | 85%
BA-29 | ISSU-052 | Employee Health and Safety Violation | High | 180 | 240 | Yes | 60%
BA-29 | ISSU-087 | Contract Dispute with Supplier | Medium | 45 | 60 | No | 80%
BA-29 | ISSU-071 | Reputational Damage due to Negative Publicity | High | 7 | 14 | Yes | 70%
BA-29 | ISSU-026 | Website Downtime | High | 1 | 1 | Yes | 100%
BA-29 | ISSU-044 | Inventory Management Issues | Medium | 5 | 7 | No | 90%
BA-29 | ISSU-063 | Exchange Rate Fluctuations | Medium | 30 | 45 | No | 75%
BA-29 | ISSU-080 | Internet Connectivity Issues | High | 3 | 4 | Yes | 85%
BA-29 | ISSU-024 | Extreme Weather Impact on Product Delivery | High | 14 | 21 | Yes | 50%
BA-29 | ISSU-039 | Workplace Harassment Complaint | Low | 60 | 90 | Yes | 80%
BA-29 | ISSU-055 | Application Development Delays | Medium | 180 | 240 | Yes | 50%
BA-29 | ISSU-007 | Privacy Breach | High | 1 | 2 | Yes | 95%
BA-29 | ISSU-046 | Asset Management Issues | Medium | 7 | 14 | No | 70%
BA-29 | ISSU-090 | Counterfeit Products | High | 10 | 14 | Yes | 60%
BA-29 | ISSU-031 | Supply Chain Disruption | High | 14 | 21 | Yes | 75%
BA-29 | ISSU-077 | Product Recall | High | 7 | 10 | Yes | 90%
BA-29 | ISSU-002 | Workplace Injury | High | 30 | 45 | Yes | 70%
LA-08 | ISSU-054 | Inadequate Project Planning | Medium | 45 | 60 | No | 80%
LA-08 | ISSU-036 | Environmental Regulation Non-Compliance | High | 60 | 90 | No | 60%
LA-08 | ISSU-068 | Machine Malfunction | Medium | 5 | 7 | Yes | 85%
LA-08 | ISSU-025 | Contract Termination by Client | High | 30 | 45 | Yes | 50%
LA-08 | ISSU-069 | Data Loss | High | 1 | 1 | Yes | 100%
LA-08 | ISSU-012 | Intellectual Property Infringement | High | 14 | 21 | Yes | 75%
LA-08 | ISSU-048 | Employee Turnover | Medium | 180 | 240 | No | 80%
LA-08 | ISSU-072 | Marketing Campaign Failure | Medium | 7 | 14 | No | 70%
LA-08 | ISSU-043 | Supplier Bankruptcy | High | 10 | 14 | Yes | 60%
LA-08 | ISSU-089 | Product Obsolescence | Medium | 45 | 60 | No | 90%
LA-08 | ISSU-034 | Cybersecurity Breach | High | 3 | 4 | Yes | 85%
LA-08 | ISSU-057 | Incorrect Shipment | Medium | 14 | 21 | Yes | 75%
LA-08 | ISSU-084 | Equipment Maintenance Delay | Medium | 60 | 90 | Yes | 50%
NM-12 | ISSU-015 | Employee Misconduct | High | 1 | 2 | Yes | 95%
NM-12 | ISSU-059 | IT Infrastructure Failure | High | 7 | 10 | Yes | 90%
NM-12 | ISSU-082 | Market Saturation | Medium | 30 | 45 | No | 80%
NM-12 | ISSU-018 | Disgruntled Customer Complaint | Low | 180 | 240 | Yes | 70%
NM-12 | ISSU-050 | Budget Overrun | High | 14 | 21 | Yes | 75%
NM-12 | ISSU-066 | Product Design Flaw | High | 7 | 14 | Yes | 90%
NM-12 | ISSU-023 | Employee Health Concerns | Medium | 30 | 45 | No | 70%
NM-12 | ISSU-032 | Delays in Government Approvals | High | 60 | 90 | No | 60%
NM-12 | ISSU-040 | Transportation Disruption | High | 5 | 7 | Yes | 85%
NM-12 | ISSU-065 | Project Scope Creep | Medium | 30 | 45 | Yes | 50%
NM-12 | ISSU-019 | Customer Dispute | High | 14 | 21 | Yes | 75%
NM-12 | ISSU-076 | Resource Shortage | High | 45 | 60 | Yes | 80%
NM-12 | ISSU-045 | Legal Dispute | High | 60 | 90 | No | 60%
NM-12 | ISSU-072 | Equipment Damage | Medium | 10 | 14 | Yes | 60%
NM-12 | ISSU-007 | Miscommunication with Stakeholders | Medium | 45 | 60 | Yes | 90%
NM-12 | ISSU-085 | Product Quality Issue | High | 3 | 4 | Yes | 85%
NM-12 | ISSU-029 | Vendor Performance Issues | Medium | 14 | 21 | Yes | 75%
NM-12 | ISSU-044 | Project Management Tool Malfunction | Medium | 60 | 90 | Yes | 50%
NM-12 | ISSU-053 | Product Liability Claim | High | 1 | 2 | Yes | 95%
NM-12 | ISSU-018 | Material Shortage | High | 7 | 10 | Yes | 90%
NM-12 | ISSU-024 | Workforce Diversity and Inclusion Issues | Medium | 30 | 45 | No | 80%
NM-12 | ISSU-071 | Website Downtime | High | 180 | 240 | Yes | 70%
NM-12 | ISSU-031 | Supply Chain Capacity Constraints | Medium | 14 | 21 | Yes | 75%
NM-12 | ISSU-026 | Unexpected Competitor Action | High | 7 | 10 | Yes | 90%
NM-12 | ISSU-039 | Cybersecurity Breach | High | 2 | 7 | Yes | 80%
NM-12 | ISSU-075 | Natural Disaster | High | 30 | 60 | No | 50%
NM-12 | ISSU-069 | Product Recalls | High | 14 | 21 | Yes | 75%
AM-02 | ISSU-012 | Regulatory Compliance Issues | High | 60 | 90 | No | 60%
AM-02 | ISSU-054 | Change in Market Conditions | High | 14 | 21 | Yes | 85%
AM-02 | ISSU-068 | Infrastructure Failure | High | 7 | 10 | Yes | 90%
AM-02 | ISSU-050 | Quality Control Failure | High | 14 | 21 | Yes | 75%
AM-02 | ISSU-011 | Intellectual Property Infringement | High | 60 | 90 | No | 60%
| ISSU-043 | Employee Turnover | Medium | 30 | 45 | Yes | 80%

## DIM_DEPENDENCY
DEPEDENCESID | PROJECTCODE | DependenceDescription | DEPEDENCESSTATUS | DEPEDENCESCOMMENTS
DI-001 | AM-02 | Ensure sufficient funding for project execution | Pending | Funding request submitted to management for approval
DI-002 | AT-01 | Complete product design before beginning manufacturing | In Progress | Design phase nearing completion, manufacturing start date tentatively set for next month
DI-003 | BA-15 | Obtain necessary government approvals before beginning construction | Delayed | Approval process is taking longer than expected, project timeline may need to be adjusted
DI-004 | BA-29 | Complete testing before launching product | On Track | Testing phase is proceeding according to schedule, no major issues detected so far
DI-005 | LA-08 | Hire additional staff to manage increased workload | In Progress | Hiring process has begun, candidate interviews scheduled for next week
DI-006 | NM-12 | Acquire necessary equipment before beginning production | On Hold | Equipment supplier is experiencing delays, delivery date has been pushed back indefinitely
DI-007 | AM-02 | Secure necessary permits before beginning construction | In Progress | Permit applications have been submitted, awaiting approval from regulatory agencies
DI-008 | AM-02 | Finalize project scope before beginning work | On Track | Project scope has been agreed upon by all stakeholders and is ready for execution
DI-009 | AM-02 | Identify potential risks and develop contingency plans | In Progress | Risk assessment is underway, contingency plans being developed based on identified risks
DI-010 | AM-02 | Train employees on new systems before launch | Delayed | Employee training sessions have been postponed due to scheduling conflicts, new dates are being arranged
DI-011 | AT-01 | Acquire necessary raw materials before beginning production | On Track | Raw material inventory is being monitored closely, reorder point set to ensure timely acquisition
DI-012 | AT-01 | Develop communication plan to keep stakeholders informed | On Track | Communication plan has been developed and is being implemented according to schedule
DI-013 | AT-01 | Finalize project timeline before beginning work | In Progress | Project timeline is being refined based on updated risk assessment and resource availability
DI-014 | AT-01 | Obtain necessary financing before beginning project | Pending | Financing options are being explored, no definitive agreement has been reached yet
DI-015 | AT-01 | Obtain necessary licenses and certifications before launch | In Progress | License and certification applications have been submitted, awaiting approval from relevant agencies
DI-016 | AT-01 | Develop quality control plan before beginning production | On Track | Quality control plan has been developed and is being implemented according to schedule
DI-017 | AT-01 | Secure necessary partnerships before launch | Delayed | Partnership negotiations are ongoing, no definitive agreement has been reached yet
DI-018 | BA-15 | Identify necessary technology and acquire before launch | On Track | Technology needs have been identified and procurement process is underway
DI-019 | BA-15 | Develop and implement safety plan before beginning work | On Track | Safety plan has been developed and is being implemented according to schedule
DI-020 | BA-15 | Identify necessary permits and obtain before launch | In Progress | Permit requirements are being researched, applications will be submitted once requirements are fully understood.
DI-021 | BA-15 | Complete vendor selection process before ordering equipment | In Progress | Vendor proposals have been received and are being evaluated, decision expected next week
DI-022 | BA-15 | Finalize project budget before beginning work | On Track | Project budget has been established and is being monitored regularly for any necessary adjustments
DI-023 | BA-15 | Identify key project milestones and deliverables | On Track | Project milestones and deliverables have been identified and documented, being monitored regularly for progress
DI-024 | BA-29 | Develop and implement training program for new employees | Delayed | Training program is being developed, but has been delayed due to unexpected staffing issues
DI-025 | BA-29 | Obtain necessary insurance before beginning work | On Track | Insurance requirements have been identified and policies have been secured, being monitored regularly for any necessary updates
DI-026 | BA-29 | Develop and implement change management plan | In Progress | Change management plan is being developed based on identified risks and potential changes to project scope
DI-027 | BA-29 | Obtain necessary approvals from stakeholders before launch | In Progress | Stakeholder approvals are being obtained, progress being monitored regularly for any delays or issues
DI-028 | BA-29 | Identify and secure necessary permits for transportation of goods | On Track | Permit requirements have been identified and applications submitted, being monitored regularly for approval status
DI-029 | BA-29 | Develop and implement project governance structure | On Track | Project governance structure has been established and is being implemented according to plan
DI-030 | BA-29 | Identify and secure necessary permits for site access and construction | In Progress | Permit requirements are being researched, applications will be submitted once requirements are fully understood
DI-031 | BA-29 | Develop and implement risk management plan | On Track | Risk management plan has been developed and is being implemented according to schedule
DI-032 | BA-29 | Obtain necessary approvals for project budget and timeline | Pending | Budget and timeline approvals are being sought from relevant stakeholders, progress being monitored regularly
DI-033 | BA-29 | Identify and secure necessary permits for use of natural resources | In Progress | Permit requirements are being researched, applications will be submitted once requirements are fully understood
DI-034 | BA-29 | Develop and implement project performance metrics | On Track | Performance metrics have been identified and are being implemented according to plan
DI-035 | BA-29 | Identify and secure necessary permits for environmental impact | In Progress | Permit requirements are being researched, applications will be submitted once requirements are fully understood
DI-036 | BA-29 | Develop and implement project communication plan | On Track | Communication plan has been developed and is being implemented according to schedule
DI-037 | BA-29 | Obtain necessary approvals for project scope and objectives | In Progress | Scope and objective approvals are being sought from relevant stakeholders, progress being monitored regularly
DI-038 | BA-29 | Identify and secure necessary permits for use of public resources | On Track | Permit requirements have been identified and applications submitted, being monitored regularly for approval status
DI-039 | BA-29 | Develop and implement project schedule and timeline | On Track | Schedule and timeline have been established and are being monitored regularly for progress
DI-040 | BA-29 | Identify and secure necessary permits for project site access and security | In Progress | Permit requirements are being researched, applications will be submitted once requirements are fully understood
DI-041 | BA-29 | Obtain necessary approvals for project funding | In Progress | Funding approvals are being sought from relevant stakeholders, progress being monitored regularly
DI-042 | LA-08 | Develop and implement project quality assurance plan | On Track | Quality assurance plan has been developed and is being implemented according to schedule
DI-043 | LA-08 | Identify and secure necessary permits for project waste management | In Progress | Permit requirements are being researched, applications will be submitted once requirements are fully understood
DI-044 | LA-08 | Develop and implement project change control process | In Progress | Change control process is being developed based on identified risks and potential changes to project scope
DI-045 | LA-08 | Obtain necessary approvals for project design and specifications | On Track | Design and specification approvals are being sought from relevant stakeholders, progress being monitored regularly
DI-046 | LA-08 | Identify and secure necessary permits for project utilities | On Track | Permit requirements have been identified and applications submitted, being monitored regularly for approval status
DI-047 | LA-08 | Develop and implement project resource allocation plan | On Track | Resource allocation plan has been developed and is being implemented according to schedule
DI-048 | LA-08 | Obtain necessary approvals for project team structure and roles | In Progress | Team structure and role approvals are being sought from relevant stakeholders, progress being monitored regularly
DI-049 | LA-08 | Identify and secure necessary permits for project site access and logistics | In Progress | Permit requirements are being researched, applications will be submitted once requirements are fully understood
DI-050 | LA-08 | Develop and implement project performance reporting system | On Track | Performance reporting system has been developed and is being implemented according to schedule
DI-051 | LA-08 | Obtain necessary approvals for project technology and equipment | On Track | Technology and equipment approvals are being sought from relevant stakeholders, progress being monitored regularly
DI-052 | LA-08 | Identify and secure necessary permits for project site restoration and cleanup | In Progress | Permit requirements are being researched, applications will be submitted once requirements are fully understood
DI-053 | LA-08 | Develop and implement project stakeholder engagement plan | On Track | Stakeholder engagement plan has been developed and is being implemented according to schedule
DI-054 | LA-08 | Obtain necessary approvals for project permits and licenses | In Progress | Permit and license approvals are being sought from relevant stakeholders, progress being monitored regularly
DI-055 | NM-12 | Identify and secure necessary permits for project transportation and logistics | In Progress | Permit requirements are being researched, applications will be submitted once requirements are fully understood
DI-056 | NM-12 | Develop and implement project procurement plan | On Track | Procurement plan has been developed and is being implemented according to schedule
DI-057 | NM-12 | Obtain necessary approvals for project testing and acceptance | On Track | Testing and acceptance approvals are being sought from relevant stakeholders, progress being monitored regularly
DI-058 | NM-12 | Identify and secure necessary permits for project safety and security | In Progress | Permit requirements are being researched, applications will be submitted once requirements are fully understood
DI-059 | NM-12 | Develop and implement project resource contingency plan | On Track | Resource contingency plan has been developed and is being implemented according to schedule
DI-060 | NM-12 | Obtain necessary approvals for project contracts and agreements | On Track | Contract and agreement approvals are being sought from relevant stakeholders, progress being monitored regularly
DI-061 | NM-12 | Identify and secure necessary permits for project site construction | In Progress | Permit requirements are being researched, applications will be submitted once requirements are fully understood
DI-062 | NM-12 | Develop and implement project communication plan | On Track | Communication plan has been developed and is being implemented according to schedule
DI-063 | NM-12 | Obtain necessary approvals for project schedules and timelines | On Track | Schedule and timeline approvals are being sought from relevant stakeholders, progress being monitored regularly
DI-064 | NM-12 | Identify and secure necessary permits for project environmental compliance | In Progress | Permit requirements are being researched, applications will be submitted once requirements are fully understood
DI-065 | NM-12 | Develop and implement project risk management plan | On Track | Risk management plan has been developed and is being implemented according to schedule
DI-066 | NM-12 | Obtain necessary approvals for project resource allocation | On Track | Resource allocation approvals are being sought from relevant stakeholders, progress being monitored regularly
DI-067 | NM-12 | Identify and secure necessary permits for project waste disposal | In Progress | Permit requirements are being researched, applications will be submitted once requirements are fully understood
DI-068 | NM-12 | Develop and implement project stakeholder communication plan | On Track | Stakeholder communication plan has been developed and is being implemented according to schedule
DI-069 | NM-12 | Obtain necessary approvals for project scope and objectives | In Progress | Scope and objective approvals are being sought from relevant stakeholders, progress being monitored regularly
DI-070 | NM-12 | Identify and secure necessary permits for project noise and vibration control | In Progress | Permit requirements are being researched, applications will be submitted once requirements are fully understood
DI-071 | NM-12 | Develop and implement project training plan | On Track | Training plan has been developed and is being implemented according to schedule
DI-072 | NM-12 | Obtain necessary approvals for project budget and financial plan | On Track | Budget and financial plan approvals are being sought from relevant stakeholders, progress being monitored regularly
DI-073 | NM-12 | Identify and secure necessary permits for project access to public land and waterways | In Progress | Permit requirements are being researched, applications will be submitted once requirements are fully understood
DI-074 | NM-12 | Develop and implement project documentation plan | On Track | Documentation plan has been developed and is being implemented according to schedule
DI-075 | NM-12 | Obtain necessary approvals for project safety plan | On Track | Safety plan approvals are being sought from relevant stakeholders, progress being monitored regularly
DI-076 | NM-12 | Identify and secure necessary permits for project air quality control | In Progress | Permit requirements are being researched, applications will be submitted once requirements are fully understood
DI-077 | NM-12 | Develop and implement project closeout plan | On Track | Closeout plan has been developed and is being implemented according to schedule
DI-078 | NM-12 | Obtain necessary approvals for project construction drawings and specifications | In Progress | Construction drawing and specification approvals are being sought from relevant stakeholders, progress being monitored regularly
DI-079 | NM-12 | Identify and secure necessary permits for project hazardous materials management | In Progress | Permit requirements are being researched, applications will be submitted once requirements are fully understood
DI-080 | NM-12 | Develop and implement project performance measurement plan | On Track | Performance measurement plan has been developed and is being implemented according to schedule
DI-081 | NM-12 | Obtain necessary approvals for project change requests | In Progress | Change request approvals are being sought from relevant stakeholders, progress being monitored regularly
DI-082 | AM-02 | Identify and secure necessary permits for project water supply and wastewater disposal | In Progress | Permit requirements are being researched, applications will be submitted once requirements are fully understood
DI-083 | AM-02 | Develop and implement project quality management plan | On Track | Quality management plan has been developed and is being implemented according to schedule
DI-084 | AM-02 | Obtain necessary approvals for project design plans and specifications | On Track | Design plan and specification approvals are being sought from relevant stakeholders, progress being monitored regularly
DI-085 | AM-02 | Identify and secure necessary permits for project site access and transportation | In Progress | Permit requirements are being researched, applications will be submitted once requirements are fully understood
DI-086 | AM-02 | Develop and implement project change management plan | On Track | Change management plan has been developed and is being implemented according to schedule

## DIM_MILESTONE
MILESTONEID | PROJECTCODE | PMNAME | MILESTONE | STARTDATE | DURATION | ENDDATE | DAYESCOMPLETED
MILESTON-1 | LA-08 |  | Conduct a thorough assessment of the meeting room | 2019-03-31 | 0 years, 0 months, 30 days | 2019-04-30 | 22
MILESTON-1 | NM-12 |  | Determine the AV system requirements and budget | 2019-08-09 | 0 years, 3 months, 21 days | 2019-11-30 | 81
MILESTON-1 | AM-02 |  | Develop a comprehensive AV system design and engineering plan | 2021-05-15 | 0 years, 4 months, 0 days | 2021-09-15 | 88
MILESTON-2 | AM-02 |  | Procure and install AV equipment, including displays, projectors, microphones, and speakers | 2021-09-15 | 0 years, 4 months, 0 days | 2022-01-15 | 88
MILESTON-1 | AT-01 |  | Test and commission the AV system to ensure it meets the project requirements and user needs | 2022-01-01 | 0 years, 2 months, 12 days | 2022-03-13 | 50
MILESTON-1 | BA-15 |  | Provide user training and support for the AV system | 2022-03-13 | 0 years, 2 months, 4 days | 2022-05-17 | 47
MILESTON-1 | BA-29 |  | Conduct a security assessment to identify vulnerabilities and risks | 2019-08-09 | 0 years, 2 months, 0 days | 2019-10-09 | 44
MILESTON-2 | LA-08 |  | Develop a comprehensive security plan and strategy | 2019-05-01 | 0 years, 1 months, 29 days | 2019-06-30 | 43
MILESTON-3 | AM-02 |  | Implement physical security measures, including access control systems, surveillance cameras, and alarms | 2019-12-09 | 0 years, 2 months, 0 days | 2020-02-09 | 45
MILESTON-4 | AM-02 |  | Deploy cybersecurity measures, including firewalls, antivirus software, and intrusion detection systems | 2020-02-09 | 0 years, 2 months, 0 days | 2020-04-09 | 44
MILESTON-5 | AM-02 |  | Develop security policies and procedures for employees and contractors | 2020-04-09 | 0 years, 2 months, 0 days | 2020-06-09 | 44
MILESTON-6 | AM-02 |  | Train employees and contractors on security protocols | 2020-06-09 | 0 years, 2 months, 0 days | 2020-08-09 | 44
MILESTON-7 | AM-02 |  | Determine the required manpower for the project | 2020-08-09 | 0 years, 2 months, 0 days | 2020-10-09 | 45
MILESTON-8 | AM-02 |  | Develop job descriptions and specifications for the required manpower | 2020-10-09 | 0 years, 2 months, 0 days | 2020-12-09 | 44
MILESTON-9 | AM-02 |  | Recruit and hire personnel | 2020-12-09 | 0 years, 2 months, 0 days | 2021-02-09 | 45
MILESTON-10 | AM-02 |  | Develop and implement a training program for the personnel | 2021-02-09 | 0 years, 2 months, 0 days | 2021-04-09 | 44
MILESTON-2 | AT-01 |  | Monitor and evaluate the performance of the personnel | 2021-04-09 | 0 years, 2 months, 0 days | 2021-06-09 | 44
MILESTON-3 | AT-01 |  | Implement a retention strategy to keep qualified personnel on the project | 2021-06-09 | 0 years, 2 months, 0 days | 2021-08-09 | 44
MILESTON-4 | AT-01 |  | Determine the crisis room requirements and budget | 2021-08-09 | 0 years, 2 months, 0 days | 2021-10-09 | 45
MILESTON-5 | AT-01 |  | Develop a comprehensive crisis room design and engineering plan | 2021-10-09 | 0 years, 2 months, 0 days | 2021-12-09 | 44
MILESTON-6 | AT-01 |  | Procure and install the necessary equipment, including communication systems, video walls, and emergency power backup | 2021-12-09 | 0 years, 2 months, 0 days | 2022-02-09 | 45
MILESTON-7 | AT-01 |  | Test and commission the crisis room to ensure it meets the project requirements and user needs | 2022-02-09 | 0 years, 2 months, 0 days | 2022-04-09 | 43
MILESTON-8 | AT-01 |  | Provide user training and support for the crisis room | 2022-04-09 | 0 years, 2 months, 0 days | 2022-06-09 | 44
MILESTON-2 | BA-15 |  | Determine the network infrastructure requirements and budget | 2022-06-09 | 0 years, 2 months, 0 days | 2022-08-09 | 44
MILESTON-3 | BA-15 |  | Develop a comprehensive network infrastructure design and engineering plan | 2022-08-09 | 0 years, 2 months, 0 days | 2022-10-09 | 44
MILESTON-4 | BA-15 |  | Procure and install the necessary equipment, including switches, routers, and servers | 2022-10-09 | 0 years, 2 months, 0 days | 2022-12-09 | 45
MILESTON-5 | BA-15 |  | Test and commission the network infrastructure to ensure it meets the project requirements and user needs | 2022-12-09 | 0 years, 2 months, 0 days | 2023-02-09 | 45
MILESTON-6 | BA-15 |  | Provide user training and support for the network infrastructure | 2023-02-09 | 0 years, 2 months, 0 days | 2023-04-09 | 42
MILESTON-7 | BA-15 |  | Evaluation and Improvemen | 2023-04-09 | 0 years, 2 months, 0 days | 2023-06-09 | 45
MILESTON-2 | BA-29 |  | Feasibility Study | 2019-08-09 | 0 years, 2 months, 0 days | 2019-10-09 | 44
MILESTON-3 | BA-29 |  | Business Case | 2019-10-09 | 0 years, 2 months, 0 days | 2019-12-09 | 44
MILESTON-4 | BA-29 |  | Stakeholder Engagement | 2019-12-09 | 0 years, 2 months, 0 days | 2020-02-09 | 45
MILESTON-5 | BA-29 |  | Procurement | 2020-02-09 | 0 years, 2 months, 0 days | 2020-04-09 | 44
MILESTON-6 | BA-29 |  | Site Survey | 2020-04-09 | 0 years, 2 months, 0 days | 2020-06-09 | 44
MILESTON-7 | BA-29 |  | Capacity Planning | 2020-06-09 | 0 years, 2 months, 0 days | 2020-08-09 | 44
MILESTON-8 | BA-29 |  | IP Addressing and Naming | 2020-08-09 | 0 years, 2 months, 0 days | 2020-10-09 | 45
MILESTON-9 | BA-29 |  | Security Planning | 2020-10-09 | 0 years, 2 months, 0 days | 2020-12-09 | 44
MILESTON-10 | BA-29 |  | Disaster Recovery and Business Continuity | 2020-12-09 | 0 years, 2 months, 0 days | 2021-02-09 | 45
MILESTON-11 | BA-29 |  | Configuration Management | 2021-02-09 | 0 years, 2 months, 0 days | 2021-04-09 | 44
MILESTON-12 | BA-29 |  | Change Management processes | 2021-04-09 | 0 years, 2 months, 0 days | 2021-06-09 | 44
MILESTON-13 | BA-29 |  | Performance Monitoring | 2021-06-09 | 0 years, 2 months, 0 days | 2021-08-09 | 44
MILESTON-14 | BA-29 |  | Incident Management | 2021-08-09 | 0 years, 2 months, 0 days | 2021-10-09 | 45
MILESTON-15 | BA-29 |  | User Acceptance Testing | 2021-10-09 | 0 years, 2 months, 0 days | 2021-12-09 | 44
MILESTON-16 | BA-29 |  | Deployment and Cut-Over | 2021-12-09 | 0 years, 2 months, 0 days | 2022-02-09 | 45
MILESTON-17 | BA-29 |  | Post-Deployment Review | 2022-02-09 | 0 years, 2 months, 0 days | 2022-04-09 | 43
MILESTON-18 | BA-29 |  | Documentation and Knowledge Management | 2022-04-09 | 0 years, 2 months, 0 days | 2022-06-09 | 44
MILESTON-19 | BA-29 |  | Decommissioning | 2022-06-09 | 0 years, 2 months, 0 days | 2022-08-09 | 44
MILESTON-3 | LA-08 |  | Procure necessary equipment | 2019-06-30 | 0 years, 3 months, 0 days | 2019-09-30 | 66
MILESTON-4 | LA-08 |  | Install crisis room infrastructure | 2019-09-30 | 0 years, 3 months, 1 days | 2019-12-31 | 67
MILESTON-5 | LA-08 |  | Test and calibrate audio-visual equipment | 2019-12-31 | 0 years, 3 months, 0 days | 2020-03-31 | 66
MILESTON-6 | LA-08 |  | Develop a contingency plan | 2020-03-31 | 0 years, 2 months, 30 days | 2020-06-30 | 66
MILESTON-7 | LA-08 |  | Train staff members | 2020-06-30 | 0 years, 3 months, 0 days | 2020-09-30 | 67
MILESTON-8 | LA-08 |  | Conduct a trial run of the meeting room | 2020-09-30 | 0 years, 3 months, 0 days | 2020-12-30 | 66
MILESTON-9 | LA-08 |  | Develop a maintenance plan | 2020-12-31 | 0 years, 3 months, 0 days | 2021-03-31 | 65
MILESTON-10 | LA-08 |  | Establish protocols for managing access to the meeting room and its systems | 2021-03-31 | 0 years, 2 months, 30 days | 2021-06-30 | 66
MILESTON-11 | LA-08 |  | Conduct a security audit | 2021-06-30 | 0 years, 3 months, 0 days | 2021-09-30 | 67
MILESTON-12 | LA-08 |  | Conduct a fire drill | 2021-09-30 | 0 years, 3 months, 1 days | 2021-12-31 | 67
MILESTON-13 | LA-08 |  | Develop a plan for backing up important data and files | 2021-12-31 | 0 years, 0 months, 30 days | 2022-01-30 | 21
MILESTON-14 | LA-08 |  | Schedule regular reviews of the project plan | 2022-02-01 | 0 years, 1 months, 30 days | 2022-03-31 | 43
MILESTON-2 | NM-12 |  | Conduct a site survey to assess the existing AV infrastructure and identify any necessary upgrades | 2019-12-01 | 0 years, 5 months, 30 days | 2020-05-31 | 130
MILESTON-3 | NM-12 |  | Develop a comprehensive AV system design and engineering plan | 2020-06-01 | 0 years, 3 months, 29 days | 2020-09-30 | 88
MILESTON-4 | NM-12 |  | Procure and install AV equipment, including displays, projectors, microphones, and speakers | 2020-10-01 | 0 years, 3 months, 30 days | 2021-01-31 | 87
MILESTON-5 | NM-12 |  | Test and commission the AV system to ensure it meets the project requirements and user needs | 2021-02-01 | 0 years, 3 months, 30 days | 2021-05-31 | 86
MILESTON-6 | NM-12 |  | Provide user training and support for the AV system | 2021-06-01 | 0 years, 3 months, 29 days | 2021-09-30 | 88
MILESTON-7 | NM-12 |  | Conduct a security assessment to identify vulnerabilities and risks | 2021-10-01 | 0 years, 3 months, 30 days | 2022-01-31 | 87
MILESTON-8 | NM-12 |  | Develop a comprehensive security plan and strategy | 2022-02-01 | 0 years, 3 months, 30 days | 2022-05-31 | 86
MILESTON-9 | NM-12 |  | Implement physical security measures, including access control systems, surveillance cameras, and alarms | 2022-06-01 | 0 years, 3 months, 29 days | 2022-09-30 | 88
MILESTON-10 | NM-12 |  | Deploy cybersecurity measures, including firewalls, antivirus software, and intrusion detection systems | 2022-10-01 | 0 years, 10 months, 8 days | 2023-08-09 | 223
Formulas:
DURATION = IF(DATEDIF([STARTDATE],[ENDDATE],"d")<0,"0 days",DATEDIF([STARTDATE],[ENDDATE],"y")&" years, "&DATEDIF([STARTDATE],[ENDDATE],"ym")&" months, "&DATEDIF([STARTDATE],[ENDDATE],"md")&" days")
DAYESCOMPLETED = NETWORKDAYS([STARTDATE],[ENDDATE])

## FACT_Project_Cost
PROJECTCODE | MILESTONEID | RISKID | ISSUEID | DEPEDENCESID | ActualCost | EV | PlannedValue | EAC | PercentComplete | ActualPercentComplete | CV | CPI | SPI | SV | DEPEDENCESSTATUS | RISKSCORE | ISSUEClosure Rate
AM-02 | MILESTON-1 | RSK-001 | ISSU-004 | DI-001 | 30000000 | 20000000 | 25000000 | 50000000 | 60% | 40% | 10000000 | 0.67 | 0.8 | -5000000 | Pending | 20 | 0.75
AT-01 | MILESTON-1 | RSK-011 | ISSU-030 | DI-002 | 40000000 | 18000000 | 45000000 | 42500000 | 70% | 45% | -10000000 | 0.875 | 0.778 | -10000000 | In Progress | 20 | 0.95
BA-15 | MILESTON-1 | RSK-015 | ISSU-062 | DI-003 | 50000000 | 50000000 | 50000000 | 50000000 | 100% | 100% | 0 | 1 | 1 | 0 | On Track | 75 | 0.8
BA-29 | MILESTON-1 | RSK-038 | ISSU-076 | DI-003 | [10 empty] | In Progress | 30 | 0.6
LA-08 | MILESTON-1 | RSK-022 | ISSU-009 | DI-005 | 38000000 | 15000000 | 38000000 | 33333333.33 | 75% | 50% | -6000000 | 0.842 | 0.842 | -2000000 | Delayed | 90 | 40%
NM-12 | MILESTON-1 | RSK-010 | ISSU-068 | DI-006 | 46000000 | 26000000 | 22000000 | 48000000 | 92.86% | 65% | -26000000 | 0.435 | 0.909 | -32000000 | In Progress | 85 | 85%
AM-02 | MILESTON-2 | RSK-006 | ISSU-086 | DI-007 | 25000000 | 18000000 | 20000000 | 42500000 | 70% | 45% | 15000000 | 0.72 | 0.9 | -2000000 | In Progress | 50 | 0.85
AM-02 | MILESTON-3 | RSK-037 | ISSU-003 | DI-008 | 35000000 | 28000000 | 32000000 | 46666666.67 | 87.5% | 70% | 7000000 | 0.8 | 0.88 | -4000000 | On Track | 20 | 0.7
AM-02 | MILESTON-4 | RSK-027 | ISSU-029 | DI-009 | 28000000 | 24000000 | 22000000 | 46666666.67 | 65% | 60% | 16000000 | 0.86 | 1.09 | 2000000 | In Progress | 60 | 0.4
AM-02 | MILESTON-5 | RSK-021 | ISSU-051 | DI-010 | 20000000 | 15000000 | 18000000 | 33333333.33 | 75% | 50% | 23000000 | 0.75 | 0.83 | -3000000 | Delayed | 80 | 0.9
AT-01 | MILESTON-2 | RSK-018 | ISSU-062 | DI-082 | 32000000 | 10000000 | 28000000 | 48000000 | 92.86% | 65% | 14000000 | 0.81 | 0.93 | -2000000 | In Progress | 90 | 90%
AT-01 | MILESTON-3 | RSK-030 | ISSU-076 | DI-083 | 22000000 | 25000000 | 30000000 | 70000000 | 62% | 53% | -25000000 | 0.5 | 0.833 | -5000000 | On Track | 30 | 75%
AT-01 | MILESTON-4 | RSK-033 | ISSU-009 | DI-084 | 42000000 | 30000000 | 40000000 | 56000000 | 75% | 68% | -12000000 | 0.714 | 0.75 | -10000000 | On Track | 40 | 85%
AT-01 | MILESTON-5 | RSK-004 | ISSU-068 | DI-085 | 38000000 | 32000000 | 38000000 | 59000000 | 84% | 89% | -6000000 | 0.842 | 0.842 | -2000000 | In Progress | 80 | 50%
AT-01 | MILESTON-6 | RSK-025 | ISSU-086 | DI-086 | 46000000 | 20000000 | 22000000 | 80000000 | 50% | 32% | -26000000 | 0.435 | 0.909 | -32000000 | On Track | 50 | 80%
AT-01 | MILESTON-7 | RSK-008 | ISSU-003 | DI-016 | 60000000 | 28000000 | 25000000 | 120000000 | 57% | 46% | -32000000 | 0.467 | 1.12 | 3000000 | On Track | 20 | 50%
AT-01 | MILESTON-8 | RSK-031 | ISSU-029 | DI-017 | 48000000 | 24000000 | 22500000 | 90000000 | 50% | 53% | -24000000 | 0.5 | 1.067 | 1500000 | Delayed | 60 | 95%
BA-15 | MILESTON-2 | RSK-013 | ISSU-046 | DI-018 | 7500000 | 7500000 | 7500000 | 7500000 | 100% | 100% | 0 | 1 | 1 | 0 | On Track | 35 | 70%
BA-15 | MILESTON-3 | RSK-003 | ISSU-090 | DI-019 | 10000000 | 10000000 | 10000000 | 10000000 | 100% | 100% | 0 | 1 | 1 | 0 | On Track | 70 | 60%
BA-15 | MILESTON-4 | RSK-026 | ISSU-031 | DI-020 | 5000000 | 5000000 | 5000000 | 5000000 | 100% | 100% | 0 | 1 | 1 | 0 | In Progress | 60 | 75%
BA-15 | MILESTON-5 | RSK-039 | ISSU-077 | DI-021 | 7500000 | 7500000 | 7500000 | 7500000 | 100% | 100% | 0 | 1 | 1 | 0 | In Progress | 5 | 90%
BA-15 | MILESTON-6 | RSK-001 | ISSU-002 | DI-022 | 5000000 | 5000000 | 5000000 | 5000000 | 100% | 100% | 0 | 1 | 1 | 0 | On Track | 85 | 70%
BA-15 | MILESTON-7 | RSK-014 | ISSU-018 | DI-023 | 7500000 | 7500000 | 7500000 | 7500000 | 100% | 100% | 0 | 1 | 1 | 0 | On Track | 45 | 95%
BA-29 | MILESTON-2 | RSK-032 | ISSU-045 | DI-018 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 90 | 75%
BA-29 | MILESTON-3 | RSK-040 | ISSU-013 | DI-019 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 50 | 85%
BA-29 | MILESTON-4 | RSK-006 | ISSU-052 | DI-020 | 0 | 0 | 0 | 0 | [6 empty] | In Progress | 30 | 60%
BA-29 | MILESTON-5 | RSK-037 | ISSU-087 | DI-021 | 0 | 0 | 0 | 0 | [6 empty] | In Progress | 40 | 80%
BA-29 | MILESTON-6 | RSK-027 | ISSU-071 | DI-022 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 80 | 70%
BA-29 | MILESTON-7 | RSK-021 | ISSU-026 | DI-023 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 25 | 100%
BA-29 | MILESTON-8 | RSK-018 | ISSU-044 | NA | 0 | 0 | 0 | 0 | [6 empty] | NA | 90 | 90%
BA-29 | MILESTON-9 | RSK-030 | ISSU-063 | NA | 0 | 0 | 0 | 0 | [6 empty] | NA | 35 | 75%
BA-29 | MILESTON-10 | RSK-033 | ISSU-080 | NA | 0 | 0 | 0 | 0 | [6 empty] | NA | 50 | 85%
BA-29 | MILESTON-11 | RSK-004 | ISSU-024 | NA | 0 | 0 | 0 | 0 | [6 empty] | NA | 5 | 50%
BA-29 | MILESTON-12 | RSK-025 | ISSU-039 | NA | 0 | 0 | 0 | 0 | [6 empty] | NA | 65 | 80%
BA-29 | MILESTON-13 | RSK-008 | ISSU-055 | NA | 0 | 0 | 0 | 0 | [6 empty] | NA | 85 | 50%
BA-29 | MILESTON-14 | RSK-031 | ISSU-007 | NA | 0 | 0 | 0 | 0 | [6 empty] | NA | 20 | 95%
BA-29 | MILESTON-15 | RSK-013 | ISSU-046 | NA | 0 | 0 | 0 | 0 | [6 empty] | NA | 80 | 70%
BA-29 | MILESTON-16 | RSK-003 | ISSU-090 | NA | 0 | 0 | 0 | 0 | [6 empty] | NA | 40 | 60%
BA-29 | MILESTON-17 | RSK-026 | ISSU-031 | NA | 0 | 0 | 0 | 0 | [6 empty] | NA | 55 | 75%
BA-29 | MILESTON-18 | RSK-039 | ISSU-077 | NA | 0 | 0 | 0 | 0 | [6 empty] | NA | 10 | 90%
BA-29 | MILESTON-19 | RSK-001 | ISSU-002 | NA | 0 | 0 | 0 | 0 | [6 empty] | NA | 60 | 70%
LA-08 | MILESTON-2 | RSK-041 | ISSU-054 | DI-042 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 20 | 20
LA-08 | MILESTON-3 | RSK-054 | ISSU-036 | DI-043 | 0 | 0 | 0 | 0 | [6 empty] | In Progress | 70 | 70
LA-08 | MILESTON-4 | RSK-059 | ISSU-068 | DI-044 | 0 | 0 | 0 | 0 | [6 empty] | In Progress | 30 | 30
LA-08 | MILESTON-5 | RSK-043 | ISSU-025 | DI-045 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 60 | 60
LA-08 | MILESTON-6 | RSK-046 | ISSU-069 | DI-046 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 45 | 45
LA-08 | MILESTON-7 | RSK-051 | ISSU-012 | DI-047 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 85 | 85
LA-08 | MILESTON-8 | RSK-049 | ISSU-048 | DI-048 | 0 | 0 | 0 | 0 | [6 empty] | In Progress | 75 | 75
LA-08 | MILESTON-9 | RSK-060 | ISSU-072 | DI-049 | 0 | 0 | 0 | 0 | [6 empty] | In Progress | 80 | 80
LA-08 | MILESTON-10 | RSK-057 | ISSU-043 | DI-050 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 15 | 15
LA-08 | MILESTON-11 | RSK-044 | ISSU-089 | DI-051 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 50 | 50
LA-08 | MILESTON-12 | RSK-056 | ISSU-034 | DI-052 | 0 | 0 | 0 | 0 | [6 empty] | In Progress | 55 | 55
LA-08 | MILESTON-13 | RSK-058 | ISSU-057 | DI-053 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 40 | 40
LA-08 | MILESTON-14 | RSK-047 | ISSU-084 | DI-054 | 0 | 0 | 0 | 0 | [6 empty] | In Progress | 90 | 90
NM-12 | MILESTON-2 | RSK-050 | ISSU-015 | DI-055 | 0 | 0 | 0 | 0 | [6 empty] | In Progress | 95 | 95
NM-12 | MILESTON-3 | RSK-055 | ISSU-059 | DI-056 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 40 | 40
NM-12 | MILESTON-4 | RSK-053 | ISSU-082 | DI-057 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 45 | 45
NM-12 | MILESTON-5 | RSK-048 | ISSU-018 | DI-058 | 0 | 0 | 0 | 0 | [6 empty] | In Progress | 30 | 30
NM-12 | MILESTON-6 | RSK-052 | ISSU-050 | DI-059 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 50 | 50
NM-12 | MILESTON-7 | RSK-045 | ISSU-066 | DI-060 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 90 | 90
NM-12 | MILESTON-8 | RSK-042 | ISSU-023 | DI-061 | 0 | 0 | 0 | 0 | [6 empty] | In Progress | 70 | 70
NM-12 | MILESTON-9 | RSK-012 | ISSU-032 | DI-062 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 35 | 35
NM-12 | MILESTON-10 | RSK-023 | ISSU-040 | DI-063 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 40 | 40
NM-12 | MILESTON-11 | RSK-005 | ISSU-065 | DI-064 | 0 | 0 | 0 | 0 | [6 empty] | In Progress | 65 | 65
NM-12 | MILESTON-12 | RSK-028 | ISSU-019 | DI-065 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 15 | 15
NM-12 | MILESTON-13 | RSK-029 | ISSU-076 | DI-066 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 85 | 85
NM-12 | MILESTON-14 | RSK-014 | ISSU-045 | DI-067 | 0 | 0 | 0 | 0 | [6 empty] | In Progress | 95 | 95
NM-12 | MILESTON-15 | RSK-032 | ISSU-072 | DI-068 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 40 | 40
NM-12 | MILESTON-16 | RSK-040 | ISSU-007 | DI-069 | 0 | 0 | 0 | 0 | [6 empty] | In Progress | 45 | 45
NM-12 | MILESTON-17 | RSK-006 | ISSU-085 | DI-070 | 0 | 0 | 0 | 0 | [6 empty] | In Progress | 30 | 30
NM-12 | MILESTON-18 | RSK-037 | ISSU-029 | DI-071 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 50 | 50
NM-12 | MILESTON-19 | RSK-027 | ISSU-044 | DI-072 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 90 | 90
NM-12 | MILESTON-20 | RSK-021 | ISSU-053 | DI-073 | 0 | 0 | 0 | 0 | [6 empty] | In Progress | 70 | 70
NM-12 | MILESTON-21 | RSK-018 | ISSU-018 | DI-074 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 35 | 35
NM-12 | MILESTON-22 | RSK-030 | ISSU-024 | DI-075 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 40 | 40
NM-12 | MILESTON-23 | RSK-033 | ISSU-071 | DI-076 | 0 | 0 | 0 | 0 | [6 empty] | In Progress | 65 | 65
NM-12 | MILESTON-24 | RSK-004 | ISSU-031 | DI-077 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 15 | 15
NM-12 | MILESTON-25 | RSK-025 | ISSU-026 | DI-078 | 0 | 0 | 0 | 0 | [6 empty] | In Progress | 85 | 85
NM-12 | MILESTON-26 | RSK-008 | ISSU-039 | DI-079 | 0 | 0 | 0 | 0 | [6 empty] | In Progress | 50 | 50
NM-12 | MILESTON-27 | RSK-031 | ISSU-075 | DI-080 | 0 | 0 | 0 | 0 | [6 empty] | On Track | 25 | 25
NM-12 | MILESTON-28 | RSK-013 | ISSU-069 | DI-081 | 0 | 0 | 0 | 0 | [6 empty] | In Progress | 80 | 80
AM-02 | MILESTON-6 | RSK-003 | ISSU-012 | DI-082 | 32000000 | 26000000 | 0 | 0 | 92.86% | [5 empty] | In Progress | 10 | 60%
AM-02 | MILESTON-7 | RSK-026 | ISSU-054 | DI-083 | 22000000 | 17,000, | 0 | 0 | [6 empty] | On Track | 90 | 85%
AM-02 | MILESTON-8 | RSK-039 | ISSU-068 | DI-084 | 0 |  | 0 | 0 | [6 empty] | On Track | 35 | 90%
AM-02 | MILESTON-9 | RSK-001 | ISSU-050 | DI-085 | 0 |  | 0 | 0 | [6 empty] | In Progress | 45 | 75%
AM-02 | MILESTON-10 | RSK-388 | ISSU-011 | DI-086 | 0 | [9 empty] | On Track | 30 | 60%